## Sheet1
Feature | Task | Owner | Estimate | Status | Actual Time
Establishment of infrastructure | Master page,Web. Create solution and web project, create master page and reference resources. | Taylor Lee, Rui Zhou | 1 hours | Done | 1 hours
| WebAPI,EF. Create WebAPI project , Create EF project using EF 6.0 | Taylor Lee, Rui Zhou | 1 hours | Done | 1 hours
| Castle Winsdor. Create Castle winsdor project to implement dependency injection | Taylor Lee, Rui Zhou | 2 hours | Done | 2 hours
Login, register, project set,dashBoard,project estimate design | HTML file generate, use Bootstrap to control style and layour | Rui Zhou,Jiang Bo Qu，Yi Zhang | 4 hours | Done | 4 hours
| Use jquery to validate input and show error messages in front end | Rui Zhou,Jiang Bo Qu，Yi Zhang | 4 hours | Done
The business of login, register, project set | User login , create new user , create project , | Rui Zhou | 4 hours | Done | 4 hours
| Check user/project name if exist. show error message frome back end | Rui Zhou | 4 hours | Done | 4 hours
DashBoard logic | Display all scrum card, project select bond. | Jiang Bo Qu | 4 hours | Done | 4 hours
| Click one scrum card and jump to Project Estimate to see the estimate result. | Jiang Bo Qu | 4 hours | Done | 4 hours
Project Estimate logic | All card should be back,you can't see other estimate until everybody chose card | Taylor Lee, Yi Zhang | 4 hours | Done | 4 hours
| User image in card when card is show up,caculate average estimate . | Taylor Lee, Yi Zhang | 4 hours | Done | 4 hours
| Refresh estimate data from webAPI, if anyone click next button, all user will redirect to DashBoard. | Taylor Lee, Yi Zhang | 4 hours | Done | 4 hours
Test | Test the whole system and fix problems to make sure it works correctly. | Rui Zhou,Jiang Bo Qu，Yi Zhang,Taylor Lee | 4 hours | Done | 8 hours
Some questions when haven't work out yet. | 1.User image has not save and display on estimate pages. |  |  | Done
| 2.One user could estimate as many times as he want. |  |  | Done
| 3.Need to add a loading picture when a user try to login system. |  |  | Done